## Quản lý Task - Capstone JS
NO | Tasks Name | Branch Name | Priority | Status | Start Build | Finish Build | % Build | Names (Dev) | Start Testing | Finish Testing | % Testing | Names (Tester) | PR / Link commit | API Endpoint / Data Link | Notes
1 | Thiết lập dự án - Khởi tạo github | main | High | Done | 2026-06-06 | 2026-06-06 | 100% | Phúc | [5 empty] | mortalhowl/capstone-js | Code theo mô hình MVC
2 | Thiết lập MockAPI |  | High | Done | 2026-06-06 | 2026-06-06 | 100% | Phúc | [5 empty] | https://6a1bcc418858a003817b3d04.mockapi.io/api/Products
3 | Xây dựng lớp đối tượng Products | feature/oop-products | Medium | Done | 2026-06-06 | 2026-06-06 | 100% | Phúc | 2026-06-06 | 2026-06-06 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/1/changes/4da51f37ecefa48c1a3da95dc84d8f0719c966d5
4 | Trang khách: Call API và hiển thị danh sách | feature/client-render-products | High | Done | 2026-06-07 | 2026-06-07 | 100% | Phúc | 2026-06-07 | 2026-06-07 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/2/changes/bcde6f4b4709d130536306286242ca26d9fa3318 | GET /Products
5 | Trang khách: Lọc sản phẩm theo loại | feature/client-filter | Medium | Done | 2026-06-07 | 2026-06-07 | 100% | Phúc | 2026-06-07 | 2026-06-07 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/3/changes/ce84e25b3f039482f3a9079dafd3cbd83d8474d5 |  | Chức năng bổ sung (ko có trong đề): thêm filter sort by price vào nhánh feature/client-filter-by-price PR: https://github.com/mortalhowl/capstone-js/pull/14/changes/ed47703067f5954fb2b0d2381a22e0216c80eee2
5.1 | Trang khách: Fix responsive của filter sản phẩm theo loại | bugfix/responsive-client-filter | Low | Done | 2026-06-24 | 2026-06-24 | 100% | Phúc | 2026-06-24 | 2026-06-24 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/16/changes/774e8e10ad3cd6f706257bbce08f91a4b486be1b
6 | Trang khách: Khởi tạo giỏ hàng & CartItem | feature/cart-init | High | Done | 2026-06-07 | 2026-06-07 | 100% | Phúc | 2026-06-07 | 2026-06-07 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/4/changes/4ca47325d8d3861cee3b667ff42c2a89ea0cc761
7 | Trang khách: Thêm vào giỏ & tăng số lượng | feature/cart-add | High | Done | 2026-06-07 | 2026-06-07 | 100% | Phúc | 2026-06-07 | 2026-06-07 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/5/changes/021d1d03e8ea0dd6bed212349100a917eccc3baa
8 | Trang khách: Hiển thị giỏ hàng (renderCart) | feature/cart-render | High | Done | 2026-06-07 | 2026-06-07 | 100% | Phúc | 2026-06-07 | 2026-06-07 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/6/changes/5ce0ecd48146d1f9e6dae50d720a619840264edb
8.1 | Trang khách: Tái cấu trúc lại theo chuẩn mô hình MVC | refactor/client-side | High | Done | 2026-06-08 | 2026-06-08 | 100% | Phúc | 2026-06-08 | 2026-06-08 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/7/changes/80b66a476b0eb0838be67f2954f108ab2bd6909c
9 | Trang khách: Tăng/giảm số lượng trong giỏ | feature/cart-update-qty | Medium | Done | 2026-06-08 | 2026-06-08 | 100% | Phúc | 2026-06-08 | 2026-06-08 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/8/changes/7c4b89c3f69b1bb7c09f50d2f1842652ae23e196
10 | Trang khách: Tính tổng tiền giỏ hàng | feature/cart-total | Medium | Done | 2026-06-08 | 2026-06-08 | 100% | Phúc | 2026-06-08 | 2026-06-08 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/9/changes/5d7bfd5653a7c63384d040ea85f9cb0553619b60
11 | Trang khách: Xóa sản phẩm khỏi giỏ | feature/cart-remove | Medium | Done | 2026-06-08 | 2026-06-08 | 100% | Phúc | 2026-06-08 | 2026-06-08 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/10/changes/e3ef26ba2cb14f68e5561a6109b4ba7931e2ba01
12 | Trang khách: Lưu & tải giỏ hàng (LocalStorage) | feature/cart-localstorage | High | Done | 2026-06-09 | 2026-06-09 | 100% | Phúc | 2026-06-09 | 2026-06-09 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/11/changes/e70d417fcebe6cd54a57486b079f750f8edb3ca9
13 | Trang khách: Thanh toán (Clear giỏ hàng) | feature/cart-checkout | High | Done | 2026-06-09 | 2026-06-09 | 100% | Phúc | 2026-06-09 | 2026-06-09 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/12/changes/2f05f93a122ecf6adf2ea4b049331a3477dc4254
13.1 | Trang khách: Fix import path - Thanh toán | bugfix/import-path-case | High | Done | 2026-06-09 | 2026-06-09 | 100% | Phúc | 2026-06-09 | 2026-06-09 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/13/changes/b926347bf60caa5f499bf9d0d4fb2d2679ebec77
13.2 | Trang khách: Fix logic thanh toán | bugfix/logic-cart-checkout | High | Done | 2026-06-24 | 2026-06-24 | 100% | Phúc | 2026-06-24 | 2026-06-24 | 100% | Phúc | https://github.com/mortalhowl/capstone-js/pull/17/changes/286110b4e1592c90baa7b59c4d3fc511a147e6db
14 | Trang quản trị: Lấy và hiển thị sản phẩm | adminpage | High | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin | GET /Products
15 | Trang quản trị: Thêm sản phẩm mới | adminpage | High | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin | POST /Products
16 | Trang quản trị: Cập nhật sản phẩm | adminpage | High | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin | PUT /Products/:id
17 | Trang quản trị: Xóa sản phẩm | adminpage | Medium | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin | DELETE /Products/:id
18 | Trang quản trị: Form Validation | adminpage | High | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin
19 | Trang quản trị: Tìm kiếm theo tên | adminpage | Medium | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin
20 | Trang quản trị: Sắp xếp theo giá | adminpage | Medium | Done | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | 2026-06-12 | 2026-06-27 | 100% | Nghĩa | https://github.com/mortalhowl/capstone-js/tree/0e435e66414eef9ff2fc4f7612d5c425bc489669/admin
21 | Deploy vercel |  | High | Done | 2026-06-06 | 2026-06-06 | 100% | Phúc
22 | Quay video demo |  | High | Done | 2026-06-28 | 2026-06-28 | 100% | Phúc